## sp3
USER STORY | TASKS | STATUS
As a developer I want to do best feature subset selection on the basis of their performance in cross validation. | Selecting any basic classification algorithm. | NS
| Selecting any suitable attribute subset selection method. | NS
| Cross validate all the possible subsets using the algorithm choosen and record their performance. | NS
| Analysing the performance of each subset. | NS
| Selecting the subset which performed best during cross-validation. | NS
As a developer I want to determine the best way to make training dataset. | Selecting the popular topics on which to collect the video lectures. | NS
| Determining the duration of clips to be extracted from the video. | NS
| Determining the suitable points in the video from where to extract clips. | NS
| Determining the no of suitable no of clips per video. | NS
| Determining the no of videos per topic that should be used. | NS
| Determining the no of instructors per topic that should be considered. | NS
| Determining the suitable length of training set required. | NS
As a developer I want to train my model using Feed-Forward Neural Networks. | Determining no of neurons in the input layer for the neural network | NS
| Determining no of neurons in the output layer for the neural network | NS
| Determining suitable no of hidden layers. | NS
| Determining suitable no of neurons in each hidden layer. | NS
| Determine the suitable activation function for the neurons. | NS
| Determining suitable batch-size for learning | NS
| Determining suitable no of epochs for learning | NS
| Determinig suitable learning rate for learning. | NS
| Finally applying mini-batch gradient descent algorithm to train the model. | NS
| Saving the parameters learned after training. | NS
As a developer I want to check the performance of my trained model on the unseen data. | Select the new dataset that was not used for training. | NS
| Applying the new dataset at the input layer of the trained neural-net. | NS
| Feed-forward each data point and evaluate the expected output. | NS
| Test each expected output against the actual label given. | NS
| Determining the accuracy of the model. | NS

## sb-bd-3
Spring backlog 3 Burnt Down chart
Date | Planned BD | Actual BD
2018-10-16 | 27 | 27 | Tasks
2018-10-18 | 25 | 27
2018-10-20 | 19 | 27
2018-10-21 | 12 | 27
2018-10-22 | 5 | 27
2018-10-23 | 0 | 27
0
Days

## sp4
SPRINT BACKLOG 4
AS A/AN | I WANT TO | SO THAT
eLearner | See the list of video lecures of a topic in decreasing order of rating | I don't have to waste my time in searching appropriate video lectures
eLearner | Determine whether the lecture is interesting or not | I get to know whether I have to watch or skip it.
eLearner | See the real time script of video lecture | I can learn more efficiently
eLearner | See the rating of a lecture | I can determine whether that lecture is appropriate for my learning or not
eLearner | See the one-line review of a video lecture | I can determine the body language of teacher in the video
eLearner | See the one-line review of a video lecture | I can determine the speaking style of teacher in the video
eLearner | See the one-line review of a video lecture | I may know whether the lecture is theoritical or practical
eLearner | See the one-line review of a video lecture | I may know whether the teacher in the video is energetic or not
eLearner | See the one-line review of a video lecture | I may know the keypoints covered in the lecture
Student | See the score of a teacher | I can determine how well he knows the subject
Student | See the review of a teacher | How much he is serious for our results
Student | See the review of a teacher | I can rely on his words
Student | See the review of a teacher | I can determine how impactful his problem solving method for our examination is.
Student | See the review of a teacher | I can request the replacement of a faculty
Student | See the review of a teacher | I can determine how much helpful and supportive he is
Student | See the review of a teacher | I may know how much affinity he.she has towards us
Student | See the review of a teacher | I may know whether he/she is concerned more about our understanding or just his teaching
Student | See the review of a teacher | I may know whether he/she is implementation oriented or just syllabus oriented
Student | See the review of a teacher | I can determine whether he/she will be able to help in executing our ideas
Student | See the review of a teacher | I may know whether he/she will treat us regardless of our scores or not
Student | See the review of a teacher | I may know whether he/she will allow discussions in the class or not
Student | See the review of a teacher | I can determine whether he/she will clear my doubts or not
Student | See the review of a teacher | I may know whether he/she will help us to achieve our goals or not
Student | See the review of a teacher | I may know whether he/she will be available for us or not when we need him
Student | See the review of a teacher | I may know whether he/she teaches from the books or from experience
HOD | See the review of a teacher | I can review a teacher
HOD | See the review of a teacher | I can classify the teachers in good, average or poor
HOD | See the review of a teacher | I can determine how much to pay him/her
HOD | See the score of a teacher | I can judge a teacher
HOD | See the score of a teacher | I can decide which subject should be alotted to a teacher
HOD | See the score of a teacher | I can determine whether a teacher is appropriate for a subject or not.
HOD | See the score of a teacher | I can determine whether a teacher is appropriate for the department or not
HOD | See the score of a teacher | I don't have to rely on sudents' feedback
HOD | See the review of a teacher | I can suggest a teacher where the improvement is required
HOD | See the review of a teacher | I can determine whether he/she will be able to engage the class or not
HOD | See the score of a teacher | I can estimate how much teaching experience he/she has
HOD | See the score of a teacher | I can estimate how much industry experience he/she has
HOD | See the review of a teacher | I can determine whether he/she plans his lectures or not
HOD | See the review of a teacher | I can determine whether he/she is guide student's about competetive exams or not
HOD | See the review of a teacher | I may know whether his teaching can make a difference
HOD | See the review of a teacher | I may know whether he/she can inspire the students or not
HOD | See the score of a teacher | I can determine how much effective his teaching methods are
HOD | See the score of a teacher | I may know whether he/she can induce enthusiasm in the class or not
HOD | See the review of a teacher | I may know whether he/she can motivate the students to study more or not
HOD | See the review of a teacher | I can determine how much he/she is relating the subject to practical life
HOD | See the score of a teacher | I can determine his presentation skills
HOD | See the score of a teacher | I can determine his communication skills
Teacher | See the score of myself | I can determine my teaching skills
Teacher | See the review of myself | I may know how much clear I am
Teacher | See the review of myself | I can determine how much explanatory I am
Teacher | See the score of myself | I can determine level of my knowledge
Teacher | See the review of myself | I may know how much the students respect me
Teacher | See the score of myself | I can determine how much stimulating to students I am
Teacher | See the review of myself | I can determine how open I am to students and their doubts
Teacher | See the score of myself | I can determine how much organized I am
Teacher | See the score of myself | I can determine which subject best suits me
Teacher | See the score of myself | I can get motivated to do better
Teacher | See the score of myself | I can improve my teaching methodologies

## sp2
SPRINT BACKLOG 2
USER STORY | TASKS | STATUS
As a developer I want to analyse the complexities of features. | Sort the features according to their level of complexities. | C
| Determining the discrete and continous features. | P
| Determining whether the features can be numerically represented. | P
| Determining the ways to extract simple features. | P
| Determining the ways to extract complex features. | NS
As a developer I want to do study of research papers and various concepts to gain more understanding about features. | Learning computer vision to find ways to extract visual features. | P
| Reading a paper "Impact of speaking styles on Engagement and Learning" | C
| Studying the correlation between Engagement of students and Learning. | C
| Studying the ways for the automatic labelling of data. | P
| Reading a paper "Recognition of student engagement from facial expression" | P
As a developer I want to select best subset of features. | Discarding the complex features which are still under study. | NS
| Discarding the features which are not numerical in nature. | NS
| Calculating correlation between all possible pairs of features. | NS
| Specifying a threshold to discard the highly correlated features. | NS
| Discarding the fetures with correlation above the threshold level. | NS
As a developer I want to discard the irrelevent features on the basis of their correlation with the corresponding labels. | Calculating correlation of each feature with the label. | NS
| Analysing the correlation values for each feature. | NS
| Specifying a threshold to define the level of correlation. | NS
| Discarding the features with corrlation below threshold level. | NS
| Selecting the optimum set of features with high level of correlation. | NS

## Product backlog
PRODUCT BACKLOG
AS A/AN | I WANT | SO THAT
Developer | To identify all possible aspects that can affect the quality of teaching | I can use them as features in my model.
Developer | To find a suitable method for the automatic labelling of video lectures | I don't have to manually label the videos.
Developer | To derive a formula for the automatic labelling of a video | I can just put some values in it and get the label.
Developer | To consider comments also to contribute in the automatic labelling of video. | I can generate more accurate formula.
Developer | To analyse the complexities of features. | I can get to know more about the features.
Developer | To do study of research papers and various concepts | I can gain more understanding about the features.
Developer | To select best subset of features. | I can discard highly correlated features.
Developer | To discard the irrelevent features on the basis of their correlation with the corresponding labels. | I can discard the features which are not affecting the labels.
Developer | To do best feature subset selection on the basis of their performance in cross validation. | I can work with minimal set of relevant features.
Developer | To determine the best way to make training dataset. | I can create my dataset,
Developer | To train my model using Feed-Forward Neural Networks. | I can train my model.
Developer | To check the performance of my trained model on the unseen data. | I can determine the accuracy of my model.
eLearner | See the list of video lecures of a topic in decreasing order of rating | I don't have to waste my time in searching appropriate video lectures
eLearner | Determine whether the lecture is interesting or not | I get to know whether I have to watch or skip it.
eLearner | See the real time script of video lecture | I can learn more efficiently
eLearner | See the rating of a lecture | I can determine whether that lecture is appropriate for my learning or not
eLearner | See the one-line review of a video lecture | I can determine the body language of teacher in the video
eLearner | See the one-line review of a video lecture | I can determine the speaking style of teacher in the video
eLearner | See the one-line review of a video lecture | I may know whether the lecture is theoritical or practical
eLearner | See the one-line review of a video lecture | I may know whether the teacher in the video is energetic or not
eLearner | See the one-line review of a video lecture | I may know the keypoints covered in the lecture
Student | See the score of a teacher | I can determine how well he knows the subject
Student | See the review of a teacher | How much he is serious for our results
Student | See the review of a teacher | I can rely on his words
Student | See the review of a teacher | I can determine how impactful his problem solving method for our examination is.
Student | See the review of a teacher | I can request the replacement of a faculty
Student | See the review of a teacher | I can determine how much helpful and supportive he is
Student | See the review of a teacher | I may know how much affinity he.she has towards us
Student | See the review of a teacher | I may know whether he/she is concerned more about our understanding or just his teaching
Student | See the review of a teacher | I may know whether he/she is implementation oriented or just syllabus oriented
Student | See the review of a teacher | I can determine whether he/she will be able to help in executing our ideas
Student | See the review of a teacher | I may know whether he/she will treat us regardless of our scores or not
Student | See the review of a teacher | I may know whether he/she will allow discussions in the class or not
Student | See the review of a teacher | I can determine whether he/she will clear my doubts or not
Student | See the review of a teacher | I may know whether he/she will help us to achieve our goals or not
Student | See the review of a teacher | I may know whether he/she will be available for us or not when we need him
Student | See the review of a teacher | I may know whether he/she teaches from the books or from experience
HOD | See the review of a teacher | I can classify the teachers in good, average or poor
HOD | See the review of a teacher | I can determine how much to pay him/her
HOD | See the review of a teacher | I can judge a teacher
HOD | See the review of a teacher | I can decide which subject should be alotted to a teacher
HOD | See the review of a teacher | I can determine whether a teacher is appropriate for a subject or not.
HOD | See the review of a teacher | I can determine whether a teacher is appropriate for the department or not
HOD | See the review of a teacher | I don't have to rely on sudents' feedback
HOD | See the review of a teacher | I can suggest a teacher where the improvement is required
HOD | See the review of a teacher | I can determine whether he/she will be able to engage the class or not
HOD | See the review of a teacher | I can estimate how much teaching experience he/she has
HOD | See the review of a teacher | I can estimate how much industry experience he/she has
HOD | See the review of a teacher | I can determine whether he/she plans his lectures or not
HOD | See the review of a teacher | I can determine whether he/she is guide student's about competetive exams or not
HOD | See the review of a teacher | I may know whether his teaching can make a difference
HOD | See the review of a teacher | I may know whether he/she can inspire the students or not
HOD | See the review of a teacher | I can determine how much effective his teaching methods are
HOD | See the review of a teacher | I may know whether he/she can induce enthusiasm in the class or not
HOD | See the review of a teacher | I may know whether he/she can motivate the students to study more or not
HOD | See the review of a teacher | I can determine how much he/she is relating the subject to practical life
HOD | See the review of a teacher | I can determine his presentation skills
HOD | See the review of a teacher | I can determine his communication skills
Teacher | See the review of myself | I can determine my teaching skills
Teacher | See the review of myself | I may know how much clear I am
Teacher | See the review of myself | I can determine how much explanatory I am
Teacher | See the review of myself | I can determine level of my knowledge
Teacher | See the review of myself | I may know how much the students respect me
Teacher | See the review of myself | I can determine how much stimulating to students I am
Teacher | See the review of myself | I can determine how much organized I am
Teacher | See the review of myself | I can determine which subject best suits me
Teacher | See the review of myself | I can improve my teaching methodologies

## sp1
SPRINT BACKLOG 1
USER STORY | TASKS | STATUS
As a developer I want to identify all possible aspects that can affect the quality of teaching | Collecting a mixture of good, bad and average quality lecture videos from youtube. | C
| Watching the videos and observing the factors that can determine quality of the lecture. | C
| Selecting the features that can be used to make our model. | C
| Categorizing the features into Audio and Visual parts. | C
As a developer I want to find a suitable method for the automatic labelling of video lectures. | Determining the external numerical aspects of a video. | C
| Considering the likes and dislikes on a video as variables | C
| Considering the no of views and date of publication of a video as variables. | C
| Considering the no of subscribers on a video as variable. | C
| Figuring out a method to evaluate score of a video using above variables. | C
As a developer I want to derive a formula for the automatic labelling of a video. | Trying (likes/dislikes) as the the formula. | C
| Trying (likes-dislikes)/(no. of views) as the formula. | C
| Trying (likes-dislikes)/(time since published) as the formula. | C
| Trying (likes-dislikes+no. of views)/(time since published) as the formula. | C
| Trying ((likes-dislikes)/(views)+(subscribers))/(time since published) as the formula. | P
As a developer I want to consider comments also to contribute in the automatic labelling of video. | Finding out the way to scrape the comments from a youtube video. | C
| Using comment scraper to download comments from youtube video as excel file. | C
| Considering sentimental analysis to extract sentiments from the comments of a video. | C
| ((likes-dislikes)/(views)+(subscribers))/(time since published)+(sentimental_value) as new formula. | C
| Analysing comments and aborting the idea of sentiment analysis on comments. | C

## sb-bd-1
Spring Backlog 01 burn down chart
Date | Planned BD | Actual BD
2018-09-04 | 19 | 19 | Tasks
2018-09-12 | 15 | 16
2018-09-11 | 12 | 12
2018-09-14 | 8 | 10
2018-09-16 | 4 | 5
2018-09-18 | 0 | 1
Days

## sb-bd-2
Spring Backlog 02 burn down chart
Date | Planned BD | Actual BD
2017-09-25 | 20 | 20 | Tasks
2017-09-28 | 15 | 20
2017-10-02 | 13 | 19
2017-10-05 | 9 | 18
2017-10-07 | 5 | 18
2017-10-09 | 0 | 17
0
Days